## Check list
1 | level complete pop-up | done | arts available
2 | level failed pop-up | done | arts available
3 | Yes/no question during monetization click. | done
4 | create server in heroku + database | done
5 | facebook friend request | done
6 | facebook share feature | done | needs level complete pop-up
8 | saving checkpoints | done
9 | Play button | done | arts given Nov 5
10 | Purchase extra hits | ?? | arts available |  | Conflicting specs. In Oct 23 power point, purchase extra hits is just a button and not pop-up
11 | Purchase extra lives | done | arts available
12 | Arrow + Arrow glow | done | arts available
13 | Star on top bar | done | integrated, the quality is poor, |  |  |  | No Glow yet
14 | Coins implementation | done |  | No facebook and database integration
15 | Run out of lives window | done
16 | life timer when run-out/epoch | done |  | No database integration, need to catch epoch upon load
17 | Objective Screen | done |  | no actual texts yet
18 | Leaderboards (per level) | done |  | together with level complete, but needs optimization
19 | highlight timer | done
20 | DOU version | done
21 | store monetize used data | done |  | store the monetization buttons used by the player
22 | Optimize leaderboards implementation | done |  | needs testing
23 | Level settings from DB , | done |  | Load every settings at load similar to previous level implementatin for level/leaderboards
24 | admin page basic level, user and money | done
25 | Monetization settings from DB | done
26 | General page settings in admin | done |  | default life, coins, etc.
27 | Leaderboard complete, display score of both players | done
28 | Admin page manual | done
29 | Replace the font in Home level screen buttons | done
30 | Baker store screen | done |  | No purchase of actual money
31 | Remove Save implementation | done
7 | sharing gifts | done
32 | Daily bunos implementation | done | Documents to be provided
33 | Text on objective screen | done | documents provided.
34 | New objective window with level leaders | done
35 | change font of button fonts and challenge number text, | done |  | please make challenge # a little larger
36 | Invite friends in no lives, +10 coins +1 lives | done
37 | add arrow to good icon | done
38 Update arrow for level 5 |  | done
39 | Unlock level implementation | done | See also the Online Shop pricing document |  |  |  | NO ARTS AVAILABLE
40 | timer for each level | done
41 | Gifts new implementation | done
42 | Board rotate | done | see Task# 369840
43 | level complete/level failed new window | done | check NewAdditions.docx |  |  | NO arts provided yet
44 | Main screen button to be merged | done | check NewAdditions.docx |  |  | NO arts provided yet
45 | loose a life when clicking the menu button | done | check NewAdditions.docx
46 | Touch event in iPad | done |  | Needs iPad emulator
47 | Level conditions | done | See Level access conditions.docx
48 | add/integrate new arts | done | see Corrections-&-update-images |  |  |  | Baker button mouse hover is WEIRD
49 | freeze 2 icon update | done
50 | Remove bronze condition | done
51 | Life system problem | - |  | need to ask Hiba for further details
52 | resized level handle

## Bug list
Bug
357176 | 1 Life Lost |  | Cannot replicate
356614 | Hits issue after restart |  | not a valid bug
356600 | Reshuffle Challenge issue | fixed
356593 | Timer Duration | fixed
356588 | Make duration longer | fixed
358617 | reshuffle board issue | fixed | include on Nov 17 release
358614 | another freeze icons issue |  | Cannot understand report, this maybe specifications
358607 | Freeze 2 icons button issue |  | Cannot replicate on live and local version
358601 | Reshuffle Board or Challenge Button issue | fixed | include on Nov 17 release
359104 | play solo after menu click button issue | fixed | include on Nov 17 release
Features
357184 | Bronze trophy condition |  | not to support, requires breaking down of code
357177 | Highlight timer | done
356647 | Level 3 Switching | done
358591 | female mascot | done | already available in live
358586 | Watch Board zone | done | to be included on Nov 17 release.